## Read Me
Nightlife Culture / UKDF Fellowship Budget & Delivery Workbook
How to use v0.3 and what changed from v0.2
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
This workbook inherits its proposition and language from the Artists Make Great Places master framework.
Control | Current position | Document hierarchy
Budget authority | Phase Budget is the application-facing source of truth. It balances to one flexible £50,000 programme resource. | 1 | Artists Make Great Places master framework | Proposition, canonical language, method, five strands, Why Carly and deck-copy authority | Locked for application drafting | Change by logged decision
Capacity authority | Internal Capacity Test is a sufficiency check only. It does not ringfence founder time or create an external-cost pot. | 2 | UKDF application draft | Full unrestricted narrative before editing to word limits | Next gateway | Inherit from master
Working rate | £500/day appears only where an application field or internal calculation requires a rate. | 3 | Main proposal deck | Persuasive, visual application-facing argument | Copy architecture drafted | Design after copy approval
Delivery window | 10–12 months. Phase outcomes govern delivery; overlap and sequencing can respond to evidence. | 4 | Detailed project-plan deck | Work packages, timeline, scope, budget, boundaries, gates and risks | Copy architecture drafted | Design after copy approval
Confirmed co-funding | ACE £0. Partner cash £0. Partner in-kind £0. No contribution is treated as real until documented. | 5 | Operating plan v0.3 | Detailed delivery and due-diligence source | Aligned | Operational authority
NCVI scope | A proposed shared evidence layer: hypothesis, evidence architecture, low-fidelity prototype, user tests and next-stage technical brief. | 6 | This workbook v0.3 | Numerical and delivery controls | Aligned | Numerical authority
Change control | Decision Log records all material changes from v0.2. The v0.2 files remain preserved.

## Dashboard
UKDF fellowship dashboard
Decision-ready view of budget, scope, capacity and boundaries
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
UKDF request | 50000 | Phase budget | 50000 | Variance | 0 | Delivery window | 10–12 months
Working rate if required | 500 | Internal founder-day reference | 52 | Place cases | 2 | Confirmed co-funding | 0
Substantive conversations | 18–24 | Paid substantial contributions | Up to 15 | Prototype users | 6–10 | ATTTF / WECA first six months | 3 days/week
Primary proposition | Nationally relevant infrastructure that increases hyperlocal power. | NCVI | Proposed shared evidence layer for the cultural life of the night | Step change | Field argument + tested method + investable institution + fundable next phase | Core deliverable through UKDF alone | Yes
Budget by phase
Code | Phase | Envelope | % |  | Control | Status | Meaning
WP1 | Frame the inquiry | 6000 | 12% |  | Budget balances | Formula | Dashboard variance must equal £0
WP2 | People, scenes and place | 9000 | 18% |  | Founder-day figure | Internal only | 52 days is a sufficiency test, not a public promise
WP3 | Follow the value | 8000 | 16% |  | Day rate | £500 if required | Budget remains phase-based
WP4 | Test what helps | 11000 | 22% |  | ACE / partners | £0 confirmed | Core delivery does not depend on other income
WP5 | Build Nightlife Culture | 7000 | 14% |  | NCVI | Proposed | Prototype and technical brief, not validated national index
WP6 | Integrate and mobilise | 6000 | 12% |  | ATTTF | Separate delivery | WECA supports CBS establishment and Bristol implementation
Programme | Stewardship, access and contingency | 3000 | 6%
TOTAL | UKDF fellowship | 50000 | 100%

## Assumptions
Assumptions & controls
Editable planning inputs; amber cells are live assumptions
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Category | Assumption | Current value | Unit | Basis / status
Programme | UKDF request | 50000 | GBP | Application ceiling
Capacity | Working founder day rate if required | 500 | GBP/day | Carly’s stated working rate
Capacity | Internal founder-days reference | 52 | days | Sufficiency check only
Timeline | Minimum delivery window | 10 | months | Application range
Timeline | Maximum delivery window | 12 | months | Application range
Parallel delivery | ATTTF / WECA commitment in first six months | 3 | days/week | Separate supported commission
Fieldwork | Place cases | 2 | places | Bounded comparative inquiry
Fieldwork | Minimum substantive conversations | 18 | conversations | Across the programme
Fieldwork | Maximum substantive conversations | 24 | conversations | Across the programme
Participation | Maximum paid substantial contributions | 15 | contributors | Payment used when the ask exceeds ordinary engagement
Prototype | Minimum intended-user tests | 6 | users | Low-fidelity test
Prototype | Maximum intended-user tests | 10 | users | Low-fidelity test
Co-funding | Confirmed ACE contribution | 0 | GBP | None confirmed
Co-funding | Confirmed partner cash | 0 | GBP | None confirmed
Co-funding | Confirmed partner in-kind value | 0 | GBP | None confirmed

## Work Packages
Work packages
Six distinct delivery jobs beneath five inquiry strands
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Code | Phase | Inquiry strand(s) | Timing | Distinct job | Phase outcome | Decision gate
WP1 | Frame the inquiry | All five | M1–2 | Turn practice and early stakeholder insight into a disciplined inquiry, ethical approach and decision framework | Inquiry frame; stakeholder/evidence maps; protocol; phase gates | G1 — Inquiry ready
WP2 | People, scenes and place | How night makes people / How people make places | M2–5 | Generate field evidence about agency, scenes, spaces and the sonic personality of place | Two place cases; field insight; reusable place lens | G2 — Place evidence sufficient
WP3 | Follow the value | Follow the value | M3–7 | Trace value, power, ownership and reinvestment, with ATTTF as one live learning case | Value-flow maps; restorative investment and advocacy implications | G3 — Value hypotheses usable
WP4 | Test what helps | Test what helps | M5–9 | Develop and test the first expression of the proposed Nightlife Cultural Value Index | Evidence architecture; low-fidelity prototype; 6–10 user tests; technical brief | G4 — Prototype route chosen
WP5 | Build Nightlife Culture | Build the institution | M7–10 | Test the institution, partnerships, offer and income architecture able to carry the work | Institutional proposition; three-part business shape; partner/capability map | G5 — Institution credible
WP6 | Integrate and mobilise | All five | M9–12 | Turn learning into a proposition that others can understand, use, back and develop | Field-backed argument; tested method; investable institution; fundable next phase | G6 — Mobilise next phase
Programme | Stewardship, access and contingency | All five | M1–12 | Protect coordination, accessibility, participant care, data stewardship and evidence-led adaptation | Decision log; programme controls; capacity to respond to discovery | All gates

## Timeline
Timeline & capacity profile
10–12 month evidence-led programme with deliberate overlap
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Phase | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Outcome month
WP1 — Frame | ● | ● | [10 empty] | M2
WP2 — People/place |  | ● | ● | ● | ● | [7 empty] | M5
WP3 — Value |  |  | ● | ● | ● | ● | ● | [5 empty] | M7
WP4 — Test / NCVI |  |  |  |  | ● | ● | ● | ● | ● |  |  |  | M9
WP5 — Institution | [6 empty] | ● | ● | ● | ● |  |  | M10
WP6 — Integrate | [8 empty] | ● | ● | ● | ● | M12
Stewardship | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | ● | M12
Internal founder-capacity profile — a planning test, not an application promise
Profile | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total / note
Founder days reference | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 4 | 4 | 52
ATTTF / WECA days per week | 3 | 3 | 3 | 3 | 3 | 3 | [6 empty] | Separate supported commission; first six months
Decision gates |  | G1 |  | G2 |  | G3 |  | G4 |  | G5 |  | G6 | Evidence-led progression

## Phase Budget
Phase budget
One flexible £50,000 programme resource; envelopes are reviewed at decision gates
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Code | Phase | Envelope | % of request | What it must make possible | Review point
WP1 | Frame the inquiry | 6000 | 12% | Founder capacity; research-design and ethics challenge; evidence and stakeholder mapping; programme setup | G1
WP2 | People, scenes and place | 9000 | 18% | Founder fieldwork and synthesis; participant contributions; access, travel, facilitation and selected research support | G2
WP3 | Follow the value | 8000 | 16% | Founder inquiry and synthesis; economic, funding or governance challenge; value-flow development | G3
WP4 | Test what helps | 11000 | 22% | Founder product/evidence leadership; measurement, data ethics, design and technical expertise; prototype and user testing | G4
WP5 | Build Nightlife Culture | 7000 | 14% | Founder institutional design; governance, commercial and funding challenge; partnership development | G5
WP6 | Integrate and mobilise | 6000 | 12% | Founder synthesis; editorial/design support; targeted next-stage technical scoping and mobilisation | G6
Programme | Stewardship, access and contingency | 3000 | 6% | Coordination, accessibility, participant care, data stewardship and evidence-led contingency | All gates
TOTAL | UKDF fellowship | 50000 | 100% | Balanced to request ceiling | Control

## Internal Capacity Test
Internal capacity sufficiency test
Reference scenarios only; no budget category is ringfenced to founder or external costs
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Rate sensitivity for the 52-day internal reference
Scenario | Reference day rate | Reference days | Founder capacity value | Flexible programme resource remaining in scenario | Meaning
Working application rate | 500 | 52 | 26000 | 24000 | Carly’s stated rate if a form requires one
Sensitivity | 575 | 52 | 29900 | 20100 | Internal planning test
Sensitivity | 650 | 52 | 33800 | 16200 | Internal planning test
Control | 500 | 52 | 26000 | 24000 | All scenarios remain subordinate to the phase budget and outcomes
Illustrative allocation of 52 founder days across programme jobs
Code | Reference days | Planning rationale |  | Control | Application effect
WP1 | 6 | Intensive framing, mapping and programme setup |  | 52 days | Shows a credible founder-capacity profile can fit the programme; phase outcomes remain the delivery promise
WP2 | 9 | Field relationships, inquiry and synthesis |  | £500/day | Used where a rate is required; does not create a ringfenced founder budget line
WP3 | 8 | Value inquiry, ATTTF learning and synthesis |  | Specialist/direct activity | Commissioned within phase envelopes according to the capability each phase needs
WP4 | 10 | Evidence/product leadership and testing |  | Gate review | Resource can move between activities when evidence changes the route
WP5 | 8 | Institutional and partnership development |  | Value for money | Specialist scopes are targeted; larger studies and production builds move to a later funded phase
WP6 | 7 | Synthesis, next phase and mobilisation
Programme | 4 | Stewardship, gates and decision log
TOTAL | 52 | Internal sufficiency check

## Specialist Inputs
Specialist inputs
Targeted expertise purchased within phase envelopes; scopes remain flexible until the evidence clarifies the need
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Need | Phase | Likely moment | Purpose | Smallest useful scope | Status | Larger work moves to
Research design and ethics | WP1 | G1 | Challenge questions, sampling, participation and claims | Short senior review plus focused revisions | To scope | Later phase only if method risk expands
Place / cultural research | WP2 | G1–G2 | Strengthen comparative design, fieldwork and synthesis | Targeted challenge, access or facilitation | To scope | Additional place cases or national fieldwork
Economic / funding / governance | WP3 | G2–G3 | Interrogate value flows, ownership and restorative investment | Selected questions and value-flow challenge | To scope | Econometrics, ROI/SROI or formal national analysis
Measurement and data ethics | WP4 | G3–G4 | Develop candidate dimensions, evidence standards and safe data principles | Senior design challenge and specification | To scope | Validation, weighting and national benchmarking
Service / information design | WP4 | G4 | Make the evidence architecture tangible and testable | Low-fidelity prototype | To scope | Production UX and platform build
Technical feasibility | WP4 / WP6 | G4 / G6 | Test data/product assumptions and estimate next-stage build | Architecture, dependencies and cost bands | To scope | Software, integrations and ongoing operation
Institutional / legal / commercial | WP5 | G5 | Test governance, partnerships, intellectual assets and income routes | Decision-point advice | To scope | Full implementation and contracted partnerships
Editorial and design | WP6 | G6 | Make field argument and mobilisation materials compelling | Priority application and partner outputs | To scope | Wider campaign and national mobilisation

## Fieldwork
Fieldwork & participation
A bounded programme sized for the £50,000 fellowship
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Activity | Volume | Purpose | Cost treatment | Evidence created | Status | Boundary
Contrasting place cases | 2 | Test people/place thesis beyond one familiar context | Within WP2 phase envelope | Two bounded case records and reusable place lens | To select at G1 | No national sample
Substantive conversations | 18–24 | Gather lived, institutional and specialist knowledge across programme | Founder capacity plus access/facilitation/transcription as needed | Consent record, notes and thematic synthesis | Planned | Across full programme, not per place
Paid substantial contributions | Up to 15 | Recognise participation where the ask exceeds ordinary stakeholder engagement | Within relevant phase envelope | Contributor input and decision trace | Planned | Payment is not assumed for every conversation
NCVI intended-user tests | 6–10 | Challenge usefulness, legitimacy, feasibility and unintended consequences | Within WP4 phase envelope | Test record and prototype revisions | Planned | Qualitative learning, not statistical validation
Rapid evidence review | Bounded | Connect live questions to existing evidence and identify gaps | Founder capacity plus targeted research support | Evidence map and source notes | Planned | No exhaustive systematic review
Accessible existing data | Selected | Test evidence dimensions and feasibility | Within WP3/WP4 envelopes | Data map and technical assumptions | To scope | No national data integration build
Travel, access and participation support | As needed | Enable credible, safe and inclusive participation | Across WP2/WP4 and programme stewardship | Access record and participation learning | To scope | Gate review protects affordability

## Funding Boundaries
Funding boundaries & additionality
Clean roles across UKDF, WECA / A Ticket to the Future, ACE and partners
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Resource | Role | Requested / confirmed | Current status | Boundary | Accounting control
UKDF | Comparative inquiry, transferable learning, NCVI R&D, Nightlife Culture institution and next-stage proposition | 50000 | Requested | Core fellowship is fully deliverable through UKDF alone | Records tagged by work package and phase
WECA / A Ticket to the Future | CBS establishment, governance transition and Bristol implementation | Separate supported commission | In delivery | Does not pay for UKDF comparative inquiry, NCVI or Nightlife Culture institutional R&D | Separate scope, records, outputs and reporting
ACE | Potential future research, sector development, resources or organisational capacity where eligible | 0 | £0 confirmed | Any award extends work through separate scope and governance | Record only after written confirmation
Partners | Potential future access, data, convening, specialist input or cash support | 0 | £0 confirmed | Core budget does not depend on partner contributions | Document cash/in-kind before inclusion

## Partner Contributions
Partner contributions register
No contribution is treated as confirmed until documented
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Potential contributor | Potential contribution | Cash confirmed | In-kind confirmed value | Evidence of confirmation | Application treatment | Owner | Status
Arts Council England | Potential future research or organisational development | 0 | 0 | None | Excluded from core budget | Carly | Unconfirmed
Place case 1 | Access, convening, local knowledge or data | 0 | 0 | None | Select through G1; no value assumed | Carly | Unconfirmed
Place case 2 | Access, convening, local knowledge or data | 0 | 0 | None | Select through G1; no value assumed | Carly | Unconfirmed
Infrastructure / data partner | Data access, technical challenge or systems insight | 0 | 0 | None | Future enhancement only | Carly | Unconfirmed
University / researcher | Methodological challenge or research collaboration | 0 | 0 | None | Future enhancement only | Carly | Unconfirmed
Sector body | Convening, user testing or mobilisation | 0 | 0 | None | Future enhancement only | Carly | Unconfirmed
TOTAL | Confirmed contributions | 0 | 0 |  | Must remain £0 until evidenced |  | Control

## Milestones & Gates
Milestones & decision gates
Evidence-led progression across the 10–12 month programme
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Gate | Timing | Decision | Evidence required | Resource decision | Owner | Status
G1 — Inquiry ready | End M2 | Approve scope, cases, ethics and evidence plan | Questions map to decisions; research burden fits resource; boundaries clear | Confirm WP2/WP3 specialist and fieldwork scopes | Carly + adviser | Planned
G2 — Place evidence sufficient | M4–5 | Confirm or adapt cases and thematic focus | Contrasting evidence; credible participation; visible people/place pathways | Adjust access, participation and synthesis support | Carly | Planned
G3 — Value hypotheses usable | M6–7 | Select value and power questions for prototype | Traceable value flows; stakeholder challenge; user implications | Confirm WP4 measurement/design inputs | Carly + specialist | Planned
G4 — Prototype route chosen | M7–8 | Choose smallest useful NCVI expression | Clear users/decisions; feasible data assumptions; ethical and affordable test | Allocate prototype and technical-feasibility resource | Carly + specialist | Planned
G5 — Institution credible | M9–10 | Confirm offer, partnerships and next-stage route | Recognisable proposition; safeguards; capability and income pathways | Confirm institutional and mobilisation inputs | Carly + adviser | Planned
G6 — Mobilise next phase | M11–12 | Approve claims, outputs, cost bands, partners and funding route | Traceability; user value; honest larger-phase scope; named next decisions | Close core programme and issue next-stage brief | Carly | Planned

## Risks & Dependencies
Risks & dependencies
Operational controls for a credible £50,000 fellowship
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
ID | Risk / dependency | Likelihood | Impact | Trigger | Control | Gate | Owner | Status
R01 | Founder overload alongside ATTTF / WECA | Medium | High | UKDF phases slip or preparation expands beyond protected capacity | Monthly capacity review; protect phase outputs; targeted support; intensify after M6 | Monthly | Carly | Open
R02 | Scope expands into a national research programme | High | High | More places, surveys, national data or impact measurement enter core phase | Use within/later scope boundary; log extensions as next-phase requirements | G1/G4 | Carly + adviser | Open
R03 | Specialist work is under-scoped | Medium | High | Advice reveals need for substantive research, technical build or legal work | Short discovery scopes; obtain cost bands; move production to next phase | Each commission | Carly | Open
R04 | Participation burden or extractive research | Medium | High | People repeat unpaid accounts without seeing value or influence | Pay substantial contributions; limit asks; return learning; show decision influence | G1–G3 | Carly | Open
R05 | NCVI promise outruns evidence | Medium | High | Language shifts from proposed evidence layer to validated index or product | Canonical definition; prototype only; publish uncertainty and technical next steps | G4 | Carly + specialist | Open
R06 | Funding boundaries blur | Low | High | ATTTF, WECA, UKDF or future funding share activity without attribution | Separate scopes, records and outputs; boundary review at every gate | All gates | Carly | Open
R07 | Institution remains founder-dependent | Medium | Medium | Proposition cannot be carried through partners or specialist capacity | Repeatable method; safeguards; business shape; capability map | G5 | Carly + adviser | Open
R08 | Language and proposition drift | Medium | High | Decks create competing definitions, slogans or method sequences | Master framework authority; decision log; cross-document audit | Every version | Carly | Controlled

## Outputs & Evidence
Outputs, evidence & new capabilities
Phase outcomes are defined by what people can do differently
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
Audience / capability | New capability | Tangible evidence | Usefulness test | WP | Timing | Status
Scenes and local advocates | Identify what creates value, gather evidence, frame shared asks and reach decisions or investment | Place lens; evidence prompts; prototype/user journeys; accessible synthesis | Advocates recognise their culture and can identify a practical next action | WP2/WP4/WP6 | M5–12 | Planned
Places | See the cultural life of the night, the conditions sustaining it and the people carrying its future | Two cases; people/place pathway; value-flow maps; NCVI evidence architecture | Place users can identify a decision the evidence improves | WP2–WP4 | M5–9 | Planned
Funders / philanthropy / responsible investors | Find locally legitimate people and propositions with clearer evidence and routes to impact | Value-flow learning; user journey; institutional and partnership proposition | Users can see where investment could strengthen cultural value and agency | WP3–WP6 | M7–12 | Planned
Researchers and sector bodies | Connect local learning to wider evidence, advocacy and methodological development | Inquiry architecture; source/evidence map; technical and ethical brief | Specialist challenge improves claims and next-stage scope | WP1/WP4/WP6 | M2–12 | Planned
Nightlife Culture | Hold and expand the method through a credible institution | Method; institutional proposition; business shape; capability/partner map | Proposition is recognisable, partnerable and less dependent on founder-only delivery | WP5/WP6 | M10–12 | Planned
Field argument | Explain nightlife as infrastructure for agency, talent and place | Synthesis grounded in two place cases, ATTTF learning and wider evidence | Claims are traceable and culturally credible | WP6 | M12 | Planned
Nightlife Cultural Value Index | Use a proposed shared evidence layer to connect local knowledge with action | Candidate dimensions; prototype; 6–10 user tests; technical/ethical next-stage brief | Users see value; limitations and future build are explicit | WP4/WP6 | M9–12 | Planned
Next phase | Move from tested proposition to larger research, validation, technology and/or rollout | Cost bands; dependencies; partner map; funding routes | Scope is honest, investable and does not depend on unconfirmed support | WP6 | M12 | Planned

## Decision Log
Decision log
Material decisions carried into v0.3; v0.2 remains preserved
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
ID | Decision area | Decision / application effect | Status | Recorded
D01 | Fellowship architecture | Retain six distinct work packages beneath five inquiry strands; each has its own question, outcome and gate | v0.2 retained | 14 Aug 2026
D02 | Fellowship duration | Use a 10–12 month window with evidence-led overlap | Updated in v0.3 | 14 Aug 2026
D03 | Founder capacity | Keep 52 days as an internal sufficiency test only; phase outcomes govern delivery; £500/day only if required | Updated in v0.3 | 14 Aug 2026
D04 | Budget ceiling | Keep the UKDF request at £50,000 and balance the phase budget to that ceiling | Retained | 14 Aug 2026
D05 | Resource presentation | Present one flexible programme resource creating Carly’s capacity and buying specialist expertise, participation and activity | Updated in v0.3 | 14 Aug 2026
D06 | Research scale | Two place cases; 18–24 conversations; up to 15 paid substantial contributions; 6–10 prototype users | Retained/refined | 14 Aug 2026
D07 | NCVI scope | Proposed shared evidence layer; hypothesis, prototype and technical brief rather than validated national index or platform | Updated in v0.3 | 14 Aug 2026
D08 | ATTTF boundary | Use ATTTF as evidence/live case; WECA supports CBS and Bristol delivery; UKDF supports transferable inquiry and institution | Updated in v0.3 | 14 Aug 2026
D09 | ACE and partner income | Confirmed ACE, partner cash and partner in-kind all remain £0 | Retained | 14 Aug 2026
D10 | Application route | Build unrestricted application narrative first, then edit into main and detailed decks | Retained | 14 Aug 2026
D11 | Deck architecture | Allow a short proposal deck and longer project-plan deck; no imposed 12-slide ceiling | Retained | 14 Aug 2026
D12 | Change control | Preserve v0.2 and create v0.3 with logged changes | Retained | 14 Aug 2026
D13 | Framework authority | Create one Artists Make Great Places master framework as authority for application, decks, plan and workbook | New in v0.3 | 14 Aug 2026
D14 | Formal studio definition | Lock the style-guide definition of Nightlife Culture as a creative policy, research and design studio | New in v0.3 | 14 Aug 2026
D15 | National and local proposition | Use Nationally relevant infrastructure that increases hyperlocal power; retire the earlier visible slogan | New in v0.3 | 14 Aug 2026
D16 | Public method | Use Listen, Map, Ideate, Prototype, Test, Refine, Expand; embed style-guide standards in descriptions | New in v0.3 | 14 Aug 2026
D17 | Why Carly | Restore dancefloor / committee room / funder meeting / evidence-base architecture with verified CV proof | New in v0.3 | 14 Aug 2026
D18 | Positive voice | Apply Joy → value → evidence → action; put boundaries after proposition and possibility | New in v0.3 | 14 Aug 2026
D19 | What UKDF moves | Name missing connective infrastructure between local cultural knowledge and evidence, policy, investment and action | New in v0.3 | 14 Aug 2026
D20 | ATTTF explanation | Assume no prior knowledge; explain problem, intervention, ownership route, Carly’s role and WECA-supported delivery | New in v0.3 | 14 Aug 2026
D21 | Institutional architecture | Retain paid consultancy, funded research and sector platform as the three-part business shape | New in v0.3 | 14 Aug 2026
D22 | Capability-led outputs | Frame outputs as new capabilities for advocates, places, funders and Nightlife Culture | New in v0.3 | 14 Aug 2026

## Source Register
Source register
Files and decisions used to consolidate the v0.3 application architecture
Version 0.3 ¦ 14 August 2026 ¦ Application working source of truth
ID | Source | Version / date | Role | Status | Location / note
S01 | Artists Make Great Places master framework and deck copy | v1.0 / 14 Aug 2026 | Proposition and language authority | Current | Created with v0.3 operating materials
S02 | Nightlife Culture — Style Guide | v1.0 / Aug 2026 | Brand, voice, formal definition and writing standards | Current | Expanded style guide
S03 | Nightlife Culture Working Deck | Aug 2026 | Method, delivery ecology, Why Carly, NCVI and business shape | Current reference | Working deck
S04 | UKDF Fellowship Proposal — Artists Make Great Places | v1.1 / Aug 2026 | Most recent pre-consolidation proposal and core thesis | Historical reference | UKDF application folder
S05 | UKDF Fellowship Operating Plan | v0.2 | Prior red-teamed operating baseline | Preserved | Superseded by v0.3
S06 | UKDF Fellowship Budget & Delivery Workbook | v0.2 | Prior numerical baseline | Preserved | Superseded by v0.3
S07 | UKDF pre-application call notes | 24 Jul 2026 | Funder steer on priority use, step change, additionality and movable problem | Current reference | Application notes
S08 | Carly Heath Creative Producer CV | 2026 v2 | Verified founder biography, delivery evidence and awards | Current reference | CV PDF
S09 | BMF Knowledge Base Synthesis | Jun 2026 | ATTTF method, evidence, governance and delivery journey | Current reference | ATTTF knowledge base